## Evidence Tracker
COMPLIANCE EVIDENCE TRACKER
Every document you need, who issues it, and where it is up to. Version 1.0, July 2026.
Document | Who issues it | Stage needed | Status | Date held | Notes
FROM THE SUPPLIER
Business licence (colour scan) | Supplier | Before deposit |  |  | Cross-check on gsxt.gov.cn
Structural engineering report, Australian wind standard | Supplier / their engineer | Before deposit |  |  | Must state wind region and classification
Full structural drawings (editable + PDF) | Supplier | Before deposit |  |  | Frame, connections, tie-downs
Steel and timber specifications + mill certificates | Supplier | Before deposit |  |  | Include coating class
Insulation R values and glazing U value / SHGC | Supplier | Before deposit |  |  | Needed for the energy assessment
Complete bill of materials | Supplier | Before deposit |  |  | Named products, not generic descriptions
Written asbestos warranty | Supplier | Before deposit |  |  | Not a substitute for testing
Packing declaration | Supplier | Before shipment |  |  | Required for all sea freight into Australia
ChAFTA Certificate of Origin | Chinese authorised body | Before shipment |  |  | Worth ~5% of customs value in avoided duty
Commercial invoice and packing list | Supplier | Before shipment |  |  | Descriptions must be accurate
Bill of lading | Shipping line | On shipment |  |  | Balance payment usually triggers on this
INDEPENDENT VERIFICATION
Pre-shipment inspection report | Inspection agency | Before balance payment |  |  | Against your written checklist
Asbestos test result, NATA accredited lab | NATA lab | Before shipment |  |  | Supplier letters are not sufficient
AUSTRALIAN PROFESSIONALS
Boundary and contour survey | Registered surveyor | Stage 1 |  |  | Certifier and engineer both need it
Geotechnical report / soil classification | Geotechnical engineer | Stage 1 |  |  | Drives footing design and cost
BAL assessment | Bushfire consultant | Stage 1 |  |  | Only if in a bushfire prone area
Wastewater site evaluation and system design | Wastewater consultant | Stage 1 |  |  | If not on mains sewer
Australian structural certification | Structural engineer | Stage 2 |  |  | Certifies the design for your site
NatHERS energy rating certificate | Accredited assessor | Stage 2 |  |  | Verify assessor at nathers.gov.au
Planning / development approval | Council | Stage 2 |  |  | Only where a DA is required
Building approval / construction certificate | Building certifier | Stage 2 |  |  | Before any work starts
Wastewater installation approval | Council | Stage 3 |  |  | Separate from building approval
Electrical certificate of compliance | Licensed electrician | Stage 4 |  |  | Work must meet Australian wiring rules
Plumbing compliance certificate | Licensed plumber | Stage 4 |  |  | WaterMark products where required
Mandatory stage inspections | Building certifier | Stage 3-4 |  |  | Follow the schedule exactly
Final certificate / occupancy approval | Building certifier | Stage 5 |  |  | This is what makes it legal to live in
PROGRESS | Items verified |  | 0 |  | of 26 tracked documents
Do not pay a deposit until every 'Before deposit' item reads VERIFIED.
DISCLAIMER: General information only. Not legal, building, engineering or customs advice. Document requirements
vary by state, territory and local government area and change without notice. Confirm the exact requirements for
your project with your building certifier and customs broker. The publisher excludes all liability to the extent permitted by law.